## How to use
AI production decision register
Companion to "Taking AI into production", AccuFind, version 0.1, September 2026. Free to reuse.
What this is
5 decisions determine whether an AI proof of concept becomes a service somebody owns. This workbook is where an agency records who owns each decision, what evidence closes it, and when it was closed.
It is a companion to the Digital Transformation Agency’s Guidance for AI proof of concept to scale, whose readiness checklist asks whether a decision register has been established. This is one.
How to use it
1. Fill in the Decision register tab at the start of the work, not the end. Decisions 1 and 2 close before the proof of concept begins.
2. Use the Baseline tab before anything is built. Once people have used the system there is no clean measurement of the process without it.
3. A decision is closed when the evidence exists and a named person has accepted it. A decision with an owner but no evidence is open.
4. The mapping tab shows which of the 12 DTA dimensions each decision covers, for agencies working to that guidance.
The 5 decisions
1. What decision changes, and who owns it. Close before the proof of concept starts.
2. What the process does now. Close before the proof of concept starts.
3. Whether the system is any good. Close at the end of the proof of concept, repeat at pilot.
4. Build, buy or tune. Close at the end of the proof of concept.
5. What production costs, and who pays. Close before the pilot starts.
A note for state and territory agencies
The DTA guidance applies to the Commonwealth and binds nobody. Outside the Commonwealth it has no standing. The 5 decisions do not depend on it, and the mapping tab is there for agencies that want the mapping.

## Decision register
# | Decision | Close it by | Owner (role) | Evidence that closes it | Status | Date closed | Notes
1 | What decision changes, and who owns it | Before the PoC starts |  | The decision named in one sentence, and the accountable role confirmed | Open
1a | That role controls or can reach the operating budget | Before the PoC starts |  | Budget line identified | Open
1b | What that person will do differently once it works | Before the PoC starts |  | Written statement of the change | Open
1c | Checked the agency use case register for duplication | Before the PoC starts |  | Register search recorded | Open
2 | What the process does now | Before the PoC starts |  | Baseline tab complete: volume, time, effort, error rate | Open
2a | Comparison group identified | Before the PoC starts |  | Group named, however imperfect | Open
2b | Stop criteria written down in advance | Before the PoC starts |  | The result that would end the work | Open
2c | What the saved time will be used for | Before the PoC starts |  | Written statement, checked after | Open
3 | Whether the system is any good | End of PoC, repeat at pilot |  | Two-axis scores, sample size, and inter-rater agreement reported | Open
3a | Retrieval and generation scored separately | End of PoC |  | Score pairs, not a single total | Open
3b | Questions the system got wrong recorded | End of PoC |  | List, not only a proportion | Open
4 | Build, buy or tune | End of PoC |  | Bought baseline established first, and beaten or not | Open
4a | If tuning proposed, the capability gap named | End of PoC |  | One sentence retrieval cannot answer | Open
4b | Recurring obligation priced | End of PoC |  | Who redoes the work on each base model turn | Open
4c | Personal information in training data checked | End of PoC |  | Privacy assessment against secondary use | Open
4d | Whole-of-government arrangements checked | End of PoC |  | GovAI or equivalent access confirmed | Open
5 | What production costs, and who pays | Before the pilot starts |  | Operating budget line and benefit owner named | Open
5a | Benefit owner sits in a business-as-usual role | Before the pilot starts |  | Role confirmed as BAU, not project | Open
5b | Process change agreed in writing | Before the pilot starts |  | Agreement from the process owner | Open
5c | Recurring costs included | Before the pilot starts |  | Evaluation, monitoring, support, model migration | Open
5d | Workforce consultation obligations checked | Before the pilot starts |  | Obligations identified and started | Open

## Baseline
Baseline worksheet
Complete before anything is built. Take the numbers from records the agency already keeps where you can, rather than from asking people.
Measure | Current process | Source of the number | Date measured | Notes
Volume (cases, documents or decisions per period)
Elapsed time per case, median
Elapsed time per case, 90th percentile
Effort per case (staff hours)
Error or rework rate
Cost per case
Backlog at a point in time
Staff doing the work (FTE)
Quality measure used today, if any
Comparison group identified
Stop criteria: the result that would end the work
What the saved time will be used for

## Mapping to DTA guidance
How the 5 decisions map to the DTA guidance
Digital Transformation Agency, Guidance for AI proof of concept to scale (2026). 3 stages: PoC, Pilot, Production. 12 dimensions.
Decision | Close it by | DTA dimensions covered
1. What decision changes, and who owns it | Before the PoC starts | Business alignment, governance, non-AI alternatives
2. What the process does now | Before the PoC starts | Business alignment, experimentation, people
3. Whether the system is any good | End of PoC, repeat at pilot | Experimentation, data, AI technique selection
4. Build, buy or tune | End of PoC | AI technique selection, architecture, technology, non-AI alternatives
5. What production costs, and who pays | Before the pilot starts | Delivery, scalability, sustainment, people, governance
The 12 DTA dimensions: business alignment, architecture, data, technology, people, governance, experimentation, delivery, scalability, sustainment, non-AI alternatives, AI technique selection.